|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCYSERVICES-FOR SUBMISSION TO TREASURY, PPDA and PUBLICATION** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| **Procuring and Disposing Entity:** | | | | | **SHEEMA DISTRICT LOCAL GOVERNMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| **Financial Year: 2024-2025** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  | | |  |  | | | | | |  | | | |  | | |  | | | |  | | |  | | | | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |  | | |
| **S/No** | | | **Subject of procurement** | **Currency** | | | | | | **Estimated cost** | | | | **Source of funding** | | | **Procurement method** | | | | **Contract Type** | | | **Pre-Qualification**  **On (Yesorno)** | | | | | **ApplyReservationScheme(Yes/No)** | | | | | | **INVITATIONANDAWARDOFBIDS** | | | | | | | | | | | | | | | | | | | | | | **Contract signing date** | | | | | | **Completion date** | | | |
| **Bid invitation date** | | | | | | | **Bid closing**  **/Opening**  **date** | | | | | **Approval evaluative report**  **date** | | | | | **Award notification date** | | | | |  | | | | | |  | | | |
| **EDUCATION DEPARTMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | | Renovation of classrooms in 5 Primary Schools of Kagazi, Bunura, Nyakashoga, Rweibare and Kyeibanga Integrated | | | | | | | UGX | | | | 159,286,179 | | Program Conditional Grant-Non wage | | | Request for Quotation | | | | Admeasurement Contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 2 | | Completion of 7 Primary Schools –Kasaana 1, Kashekuro Model P/S ,Nyakanyinya, Rutoma Full Gosipel, Kyabahija Kyabuharambo P/S and Rwengiri P/S | | | | | | | UGX | | | | 91,000,000 | | Program Conditional Grant | | | Request for Quotation | | | | Admeasurement Contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 3 | | Construction of 8 stance VIP latrine at Nyakwebundika P/s | | | | | | | UGX | | | | 45,000,000 | | Program Conditional Grant | | | Request for Quotation | | | | Admeasurement Contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 4 | | Completion of 2 classroom block at Matsya P/S | | | | | | | UGX | | | | 52,285,391 | | Program Conditional Grant | | | Request for Quotation | | | | Admeasurement Contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 5 | | Construction of two classroom block at St Jude P/S | | | | | | | UGX | | | | 65,725,670 | | SFG | | | Request for Quotation | | | | Admeasurement Contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 6 | | Procurement of ICT Equipment for Ryakasinga CHE | | | | | | | UGX | | | | 165,000,000 | | UGIFT | | | Request for Quotation | | | | Admeasurement Contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 7 | | Procurement of Science Kits for Ryakasinga CHE | | | | | | | UGX | | | | 56,047,000 | | UGIFT | | | Request for Quotation | | | | Admeasurement Contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 8 | | Procurement of office stationery | | | | | | | UGX | | | | 2,000,000 | | None wage | | | Open Bidding | | | | Frame work contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 8 | | Repair and maintenance of Vehicles and motorcycle | | | | | | | UGX | | | | 18,000,000 | | None wage | | | Open Bidding | | | | Frame work contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 9 | | Construction of Ryakasinga Seed School | | | | | | |  | | | | 496,113,909 | | UGIFT | | | Open Bidding | | | | Admeasurement Contract | | | Yes | | | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | | |  | | | |  | |  | | |  | | | |  | | |  | | | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| **HEALTH DEPARTMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  | |  | | | | | |  | | |  | | | |  | | |  | | | |  | | | | |  | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 1 | | Construction of 4 in one staff house at Bugongi H C III | | | | | | UGX | | | 43,659,279 | | | | PHC DEV’T | | | Request for Quotation | | | | Admeasurement Contract | | | | | Yes | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | |  | | |  | | | |  | | |  | | | |  | | | | |  | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 2 | | Construction of 5 stance lined VIP Latrine at Shuuku H C IV | | | | | | UGX | | | 20,000,000 | | | | PHC DEV’T | | | Request for Quotation | | | | Admeasurement Contract | | | | | Yes | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | |  | | |  | | | |  | | |  | | | |  | | | | |  | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 3 | | Procurement of Medical equipment to Kyeihara HC III | | | | | | UGX | | | 150,000,000 | | | | PHC DEV’T | | | Request for Quotation | | | | Lumpsum contract | | | | | Yes | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | |  | | |  | | | |  | | |  | | | |  | | | | |  | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 4 | | Procurement of Medical equipment to Mabaare HC III | | | | | | UGX | | | 150,000,000 | | | | PHC DEV’T | | | Request for Quotation | | | | Lumpsum contract | | | | | Yes | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | |  | | |  | | | |  | | |  | | | |  | | | | |  | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 5 | | Supply of fuel | | | | | | UGX | | | 26,835,348 | | | | PHC DEV’T | | | Open Bidding | | | | Frame work contract | | | | | Yes | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | |  | | |  | | | |  | | |  | | | |  | | | | |  | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 6 | | Supply of stationery | | | | | | UGX | | | 2,000,000 | | | | PHC DEV’T | | | Open Bidding | | | | Frame work contract | | | | | Yes | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | |  | | |  | | | |  | | |  | | | |  | | | | |  | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 7 | | Repair of departmental Vehicles | | | | | | UGX | | | 6,000,000 | | | | PHC DEV’T | | | Open Bidding | | | | Frame work contract | | | | | Yes | | | No | | | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  | |  | | | | | |  | | |  | | | |  | | |  | | | |  | | | | |  | | |  | | |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| **PLANNING DEPARTMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 1 | construction of 8 stance with urinal ground lined pit latrine at Nyakambu P/S | | | | | UGX | | | | | 45,000,000 | | | | DDEG | | | | Request for Quotation | | | Admeasurement Contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Renovation of RDCs office | | | | | UGX | | | | | 15,000,000 | | | | DDEG | | | | Request for Quotation | | | Admeasurement Contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Construction of Administration block at the district headquarters | | | | | UGX | | | | | 21,163,563 | | | | DDEG | | | | Request for Quotation | | | Admeasurement Contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Supply of stationery | | | | | UGX | | | | | 4,000,000 | | | | DDEG | | | | Open Bidding | | | Frame work contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 5 | Supply fuel | | | | | UGX | | | | | 21,863,766 | | | | DDEG | | | | Open Bidding | | | Frame work contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 6 | procurement of a laptop | | | | | UGX | | | | | 2,500,000 | | | | DDEG | | | | Micro Procurement | | | Lumpsum | | | | Yes | | | | Yes | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 7 | procurement of a photocopier for council | | | | | UGX | | | | | 4,500,000 | | | | DDEG | | | | Micro Procurement | | | Lumpsum | | | | Yes | | | | Yes | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 8 | Telecommunications | | | | | UGX | | | | | 3,000,000 | | | | DDEG | | | | Micro Procurement | | | Lumpsum | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **PRODUCTION** **DEPARTMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 1 | Supply of Fuel | | | | | UGX | | | | | 104,110,326 | | | | PMG/AEG/SSI | | | | Open Bidding | | | Frame work contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Supply of Stationery | | | | | UGX | | | | | 3,500,000 | | | | PMG/AEG/SSI | | | | Open Bidding | | | Frame work contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Supply of computer | | | | | UGX | | | | | 4,000,000 | | | | PMG/AEG/SSI | | | | Micro Procurement | | | Lumpsum | | | | Yes | | | | Yes | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Supply of Agricultural supplies | | | | | UGX | | | | | 1,000,000 | | | | LR | | | | Micro Procurement | | | Lumpsum | | | | Yes | | | | Yes | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 5 | Rehabilitation of one acre of banana | | | | | UGX | | | | | 6,000,000 | | | | PMG DEVT | | | | Micro Procurement | | | Admeasurement Contract | | | | Yes | | | | Yes | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 6 | Construction of pig sty structure | | | | | UGX | | | | | 39,060,000 | | | | AEG DEVT | | | | Request for quotation | | | Admeasurement Contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 7 | Installation of small scale irrigation equipment | | | | | UGX | | | | | 178,217,164 | | | | AEG | | | | Request for quotation | | | Admeasurement Contract | | | | Yes | | | | No | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 8 | Establishment of one acre of coffee | | | | | UGX | | | | | 6,338,227 | | | | AEG DEVT | | | | Micro Procurement | | | Admeasurement Contract | | | | Yes | | | | Yes | | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | | |  | |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **WATER SECTOR** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 1 | Construction of rain water harvesting system at Bigona p/s in Rugarama s/c and Kyeibanga Primary school in Kitagata Sub county | | | | | | UGX | | | | | 60,00,000 | | | | DWSCDG | | | | Request for quotation | | | Admeasurement Contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Extension of Nshongi piped water to Bwayegamba in Kigarama Sub County | | | | | | UGX | | | | | 90,000,000 | | | | DWSCDG | | | | Request for quotation | | | Admeasurement Contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Extension of Bwehundu piped water to Kajju in Kigarama Sub County | | | | | | UGX | | | | | 186,000,000 | | | | DWSCDG | | | | Request for quotation | | | Admeasurement Contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Rehabilitation of Kyeihara Rain Water Harvesting Tank, Construction of 3 protected springs in Rugarama S/C and Rehabilitation of 3 protected springs | | | | | | UGX | | | | | 52,000,000 | | | | DWSCDG | | | | Request for quotation | | | Admeasurement Contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 5 | Collection of Water Sample for 30 Old Sources and carrying out tests on every source, and carrying out water quality testing for 6 new sources | | | | | | UGX | | | | | 8,200,000 | | | | DWSCDG | | | | Request for quotation | | | Lumpsum contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 5 | Procurement of fuel and lubricants for office operations | | | | | | UGX | | | | | 3,330,000 | | | | DWSCDG | | | | Open Bidding | | | Frame work contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 6 | Operation & Maintenance of office computers, photocopier and printers | | | | | | UGX | | | | | 1,600,000 | | | | DWSCDG | | | | Micro Procurement | | | Frame work contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 7 | Procurement of office stationery | | | | | | UGX | | | | | 1,600,000 | | | | DWSCDG | | | | Micro Procurement | | | Frame work contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 8 | Operation and maintenance of office vehicle and motorcycle | | | | | | UGX | | | | | 7,500,000 | | | | DWSCDG | | | | Open Bidding | | | Frame work contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
| **WORKS (ROADS)** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Supply of fuel, Murram and concrete culverts for light Grading of Kasaana –Kyeihara road in Kasaana S/C (7km) | | | | | | UGX | | | | | 83,799,296 | | | | URF | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Supply of fuel, Murram and concrete culverts for maintenance of Kyarwera-Kasaana road in Kasaana S/C (8km) | | | | | | UGX | | | | | 89,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Supply of fuel, Murram and concrete culverts for maintenance of Kyarwera –Kishabya and a spur from Bagashes home to Kirundo in Shuuku S/C (7km) road | | | | | | UGX | | | | | 136,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Supply of fuel, Murram and concrete culverts for maintenance of Migiina-Rwengiri-Buringo in Kigarama S/C 10km road | | | | | | UGX | | | | | 235,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 6 | Supply of fuel and Murram for maintenance of Muziira-Kitakure-Migyerebiri- Matsyoro in Kyangyenyi S/C 10km | | | | | | UGX | | | | | 60,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 7 | Supply of fuel, Murram, and concrete culvert for maintenance of Buraro-Kanuuka in Kitagata T/C 4km road | | | | | | UGX | | | | | 64,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 8 | Supply of fuel and Murram swamp filing of Orujeebe swamp along Nyakabiriizi –Kyeibanga road | | | | | | UGX | | | | | 137,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 9 | Supply of fuel, murram and concrete culverts for maintenance of Nyakambu-Nyabwiina-Kangore in Masheruka S/C 10km | | | | | | UGX | | | | | 99,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 10 | Supply of fuel, murram and culverts for maintenance of Kamurinda-Kakindo Kalyango in Kitagata T/C 14km | | | | | | UGX | | | | | 98,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 11 | Supply of fuel, murram and concrete culverts for maintenance of Nyakarama –Bigona-Irashagye in Rugarama 6km | | | | | | UGX | | | | | 126,000,000 | | | | PDG | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 12 | Supply and installation of culverts at Masheruka SS approach | | | | | | UGX | | | | | 8,000,000 | | | | URF | | | | Micro procurement | | | Admeasurement contract | | | | Yes | | | Yes | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 13 | Repair and maintenance of heavy machines and department vehicle | | | | | | UGX | | | | | 241,527,819 | | | | URF | | | | Open bidding | | | Frame work contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 14 | Supply of fuel for Office Operations | | | | | | UGX | | | | | 50,858,346 | | | | URF | | | | Open bidding | | | Frame work contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 13 | Supply of fuel for district roads committee | | | | | | UGX | | | | | 16,000,000 | | | | PDG/URF | | | | Force Account Mechanism | | | Admeasurement contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 14 | Supply of office stationery | | | | | |  | | | | | 2,000,000 | | | | URF | | | | Open bidding | | | Frame work contract | | | | Yes | | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | |  | | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
|  | **STATUTORY DEPARTMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1. | provision of welfare services | | | | | | UGX | | | | | 4,800,000 | | | | LR | | | | Bid Opening | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | supply of stationery for PDU and District Service Commission | | | | | | UGX | | | | | 8,970,000 | | | | LR | | | | Bid Opening | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Repair of vehicles for District Chairperson | | | | | | UGX | | | | | 3,000,000 | | | | LR | | | | Bid Opening | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Supply of small office equipments | | | | | | UGX | | | | | 560,000 | | | | LR | | | | micro procurement | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 5 | Advertising services (District Service Commission and PDU) | | | | | | UGX | | | | | 6,400,000 | | | | LR | | | | Bid Opening | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 6 | supply of Fuel | | | | | | UGX | | | | | 16,600,000 | | | | LR | | | | micro procurement | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **ADMINISTRATION DEPARTMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Procurement of fuel and lubricants | | | | | | UGX | | | | | 15,000,000 | | | | Unconditional Grant | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Maintenance of vehicles | | | | | | UGX | | | | | 10,000,000 | | | | Unconditional Grant | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Procurement f stationery | | | | | | UGX | | | | | 8,000,000 | | | | Unconditional Grant | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Procurement of office equipment | | | | | | UGX | | | | | 2,000,000 | | | | Unconditional Grant | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **COMMUNITY BASED SERVICES** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Purchase of office stationery | | | | | | UGX | | | | | 2,110,000 | | | | non wage | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Supply of meals and refreshment | | | | | | UGX | | | | | 4,000,000 | | | | Conditional Grant | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Supply of fuel for office operations | | | | | | UGX | | | | | 2,700,800 | | | | Non Wage and LR | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **FINANCE DEPARTMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Supply of fuel | | | | | | UGX | | | | | 30,000,000 | | | | Non Wage and LR | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Supply of stationery | | | | | | UGX | | | | | 12,750,000 | | | | Non Wage and LR | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Supply of meals and welfare services | | | | | | UGX | | | | | 2,600,000 | | | | Non Wage and LR | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **TRADE AND INDUSTRY DEPARTMENT** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Supply of fuel for office operations | | | | | | UGX | | | | | 3,000,000 | | | | Non wage | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **DISTRICT SERVICE COMMISSION** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Supply of fuel | | | | | | UGX | | | | | 3,500,000 | | | | Non wage | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Supply of stationery | | | | | | UGX | | | | | 1,200,000 | | | | Non wage | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Supply of meals and releshment | | | | | | UGX | | | | | 2,770,000 | | | | Non wage | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | 16/8/2024 | | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | |  | | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **SHUUKU TOWN COUNCIL** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Procurement of stationery | | | | | | UGX | | | | | 2,770,000 | | | | Non wage | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Procurement of fuel | | | | | | UGX | | | | | 2,770,000 | | | | Non wage | | | | Open Bidding | | | framework contract | | | | | No | | Yes | No | | | | | | | | 5/8/2024 | | | | | | | 16/8/2024 | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Maintenance and servicing of motor vehicles | | | | | | UGX | | | | | 2,770,000 | | | | Non wage | | | | Open Bidding | | | framework contract | | | | | No | | Yes | No | | | | | | | | 5/8/2024 | | | | | | | 16/8/2024 | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **BUGONGI TOWN COUNCIL** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Renovation of CBS & Production offices and tiling Council hall | | | | | | UGX | | | | | 6,500,000 | | | | DDEG | | | | Micro Procurement | | | Admeasurement | | | | | Yes | | Yes | | | | 5/8/2024 | | | | | | | 16/8/2024 | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Supply of Fuel for light grading 26km | | | | | | UGX | | | | | 48,000,000 | | | | URF | | | | Open Bidding | | | framework contract | | | | | Yes | | No | | | | 5/8/2024 | | | | | | | 16/8/2024 | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Supply of 12 pieces 900mm culverts | | | | | | UGX | | | | | 15,000,000 | | | | URF | | | | Open Bidding | | | framework contract | | | | | Yes | | No | | | | 5/8/2024 | | | | | | | 16/8/2024 | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Fuel for council day to day operations including garbage collection | | | | | | UGX | | | | | 8,000,000 | | | | LR/UCG | | | | Open Bidding | | | framework contract | | | | | Yes | | No | | | | 5/8/2024 | | | | | | | 16/8/2024 | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 5 | Routine mechanical maintenance of council trucks | | | | | | UGX | | | | | 16,000,000 | | | | Road fund | | | | Open Bidding | | | framework contract | | | | | Yes | | No | | | | 5/8/2024 | | | | | | | 16/8/2024 | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 6 | Procurement of laptop for finance department | | | | | | UGX | | | | | 1,300,000 | | | | Road fund | | | | Open Bidding | | | framework contract | | | | | Yes | | Yes | | | | 5/8/2024 | | | | | | | 16/8/2024 | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **KASAANA SUB COUNTY** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Procurement and installation of culverts | | | | | | UGX | | | | | 6,000,000 | | | | Road fund | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Construction of slaughter slab | | | | | | UGX | | | | | 5,000,000 | | | | Road fund | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **KIGARAMA SUB COUNTY** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Supply of10,000 Ltr plastic water tank to Bwayegambya p/s | | | | | | UGX | | | | | 3,000,000 | | | | Road fund | | | | Open Bidding | | | Lumpsum | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Supply of10,000 Ltr plastic water tank to Nyakashonga P/s | | | | | | UGX | | | | | 3,000,000 | | | | Road fund | | | | Open Bidding | | | Lumpsum | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **MASHERUKA SUB COUNTY** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Roofing of Administration Block at the Sub County headquarters | | | | | | UGX | | | | | 2,000,000 | | | | DDEG | | | | Micro Procurement | | | Admeasurement | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Supply of office stationery | | | | | | UGX | | | | | 200,000 | | | | DDEG | | | | Micro Procurement | | | Admeasurement | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **KITAGATA SUB COUNTY** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | purchase of a computer | | | | | | UGX | | | | | 3,000,000 | | | | DDEG | | | | Micro Procurement | | | Lump sum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | supply, installation and construction of end structures for the reinforced pipe culvert | | | | | | UGX | | | | | 7,894,000 | | | | Road fund | | | | Open Bidding | | | framework contract | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **KITAGATA** **TOWN COUNCIL** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Supply of assorted office stationery | | | | | | UGX | | | | | 2,000,000 | | | | LR | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Procurement of one laptop | | | | | | UGX | | | | | 1,600,000 | | | | DDEG | | | | Micro procurement Bidding | | | framework contract | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Supply of fuel ,oils and lubricants for road works | | | | | | UGX | | | | | 22,000,000 | | | | Road fund | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Procurement and installation of culverts | | | | | | UGX | | | | | 2,800,000 | | | | Road fund | | | | Micro procurement | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **KYANGYENYI SUB COUNTY** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Procurement of desks for 7 primary schools | | | | | | UGX | | | | | 4,943,050 | | | | DDEG | | | | Micro procurement | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 2 | Procurement of desk top computer | | | | | | UGX | | | | | 2,500,000 | | | | DDEG | | | | Micro procurement | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 3 | Construction of waste pit at Matsyoro HC II | | | | | | UGX | | | | | 1,500,000 | | | | LR | | | | Micro procurement | | | framework contract | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| 4 | Mechanize of roads(Kyanemba-Ryamsa 2.5km,Kyakahungu I and ii -Kinyinya TC 2KM ,RUSHAMBYA-RYAKAHUNGU I 2.5KM | | | | | | UGX | | | | | 14,166,120 | | | | Road fund | | | | Open Bidding | | | framework contract | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | 10/12/2024 | | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | |  | | | | | |
| **RUGARAMA SUB COUNTY** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Procurement and installation of rain water harvesting tank | | | | | | UGX | | | | | 3,505,000 | | | | DDEG | | | | Micro Procurement | | | Admeasurement | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 2 | Rehabilitation of slaughter slab | | | | | | UGX | | | | | 1,500,000 | | | | DDEG | | | | Micro Procurement | | | Admeasurement | | | | | Yes | | Yes | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 3 | Procurement of fuel | | | | | | UGX | | | | | 14,793,000 | | | | Road fund | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 4 | Rehabilitation of monthly market at Kagati | | | | | | UGX | | | | | 2,005,000 | | | | LR | | | | Micro Procurement | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| **MASHERUKA TOWN COUNCIL** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Supply & installation of the gate at mabare HC III | | | | | | UGX | | | | | 2,000,000 | | | | PHC | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 2 | Supply of fuel | | | | | | UGX | | | | | 28,00,000 | | | | Road fund | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 3 | Supply and installation of culverts | | | | | | UGX | | | | | 9,000,000 | | | | Road fund | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 4 | Supply of 3 twin seater desks to Masheruka modern pls. | | | | | | UGX | | | | | 4,000,000 | | | | DDEG | | | | Micro Procurement | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 5 | Purchase of cupboard | | | | | | UGX | | | | | 1,000,000 | | | | DDEG | | | | Micro Procurement | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 6 | Grading of Kabutsye-Katojo Nyakiborera-Mukono Kanyegangye Centre Business District 28km | | | | | | UGX | | | | | 30,000,000 | | | | URF | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| **KAKINDO TOWN COUNCIL** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | processing of Town Council Land Title | | | | | | UGX | | | | | 2,000,000 | | | | URF | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 2 | stone pitching of CBD trenches in the Town Council | | | | | | UGX | | | | | 3,752,747 | | | | URF | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 3 | light grading of 5km Kamurinda-Kakindo road | | | | | | UGX | | | | | 4,000,000 | | | | URF | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 4 | light grading of 1.5km Rweibare play ground Tibazindwa Katooma road | | | | | | UGX | | | | | 1,996,000 | | | | URF | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 5 | light grading of 4.7 Kakindo Nyakabiriizi Kifunjo Bwiina road | | | | | | UGX | | | | | 5,066,000 | | | | URF | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 6 | light grading of 5km Kakindo Rweibare Mushanju road | | | | | | UGX | | | | | 6,270,000 | | | | URF | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 7 | light grading of 2km Rweibare s s Rukangiro Mugumya road | | | | | | UGX | | | | | 2,708,385 | | | | URF | | | | Force Account | | | Admeasurement | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| **DISPOSAL OF ABSOLETE ASSETS** | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| 1 | Disposal of old Motorcycles | | | | | | UGX | | | | | 600,000 | | | | Local Revenue | | | | Auctioning | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 2 | Disposal of old Vehicles | | | | | | UGX | | | | | 8,000,000 | | | | Local Revenue | | | | Auctioning | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 3 | Disposal of milling machine | | | | | | UGX | | | | | 2,800,000 | | | | Local Revenue | | | | Auctioning | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 4 | Disposal of scraps | | | | | | UGX | | | | | 3,000,000 | | | | Local Revenue | | | | Auctioning | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 5 | Disposal of eucalyptus trees at Rukaragwe in Bugongi T/C | | | | | | UGX | | | | | 8,000,000 | | | | Local Revenue | | | | Public Bidding | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 6 | Disposal of cows at Rubaare farm | | | | | | UGX | | | | | 16,300,000 | | | | Local Revenue | | | | Public Bidding | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 7 | Disposal of old computers and type writer | | | | | | UGX | | | | | 670,000 | | | | Local Revenue | | | | Auctioning | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 8 | Leasing of Rwanama Land | | | | | | UGX | | | | | 5,070,000 | | | | Local Revenue | | | | Public Bidding | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
| 9 | Leasing of land at Nyanga- Kakunyu –Sheema Municipality | | | | | | UGX | | | | |  | | | | Local Revenue | | | | Public Bidding | | | Lumpsum | | | | | Yes | | No | 5/8/2024 | | | | | | | | 16/8/2024 | | | | | | | 23/8/2024 | | | | | 5/9/2024 | | | | | 10/9/2024 | | | | | | 10/12/2024 | | | | |
|  |  | | | | | |  | | | | |  | | | |  | | | |  | | |  | | | | |  | |  |  | | | | | | | |  | | | | | | |  | | | | |  | | | | |  | | | | | |  | | | | |
|  | **Prepared by** | | | | | |  | | | | | Name: | | | |  | | | | | | | | | | | | | | | | | | | | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | | Signature: | | | |  | | | | | | | | | | | | | | | | | | | | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | | Designati  on: | | | | Senior Procurement Officer | | | | | | | | | | | | | | | | | | | | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | | Date: | | | |  | | | | | | | | | | | | | | | | | | | | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  | **Approved by** | | | | | |  | | | | | Name: | | | |  | | | | | | | | | | | | | | | | | | | | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | | Signature: | | | |  | | | | | | | | | | | | | | | | | | | | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | | Designati  on: | | | | Accounting Officer | | | | | | | | | | | | | | | | | | | | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | | | | | Date: | | | |  | | | | | | | | | | | | | | | | | | | | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | |